Rakhine WASH Cluster

MoM Rakhine WASH Cluster Meeting

Date:   	04/09/2015

Venue: 	UNICEF

Time: 	09.00 – 10.30

Chair: 	Rakhine WASH cluster coordinator

Attendees:

| Name | Designation | Organisation | Email | Phone |
| --- | --- | --- | --- | --- |
| Michael Keize | Emergency Coordinator | MSF | myanmar-logco@oca.msf.org | 0925089430 |
| Rob Trigwell | HRC | IRC | robert.trigwell@rescue.org | 09254380427 |
| Helen Salvestrin | Rakhine WASH cluster coordinator | UNICEF | helensalvestrin@hotmail.com | 09263835047 |
| Virgilio Joya | Rakhine Program Manager | Oxfam | vjoya@oxfam.org.uk | 0936491451 |
| Cedric Mascre | WASH consultant | SCI | cedric.mascre@savethechildren.org | 09262188771 |
| Olivier Hariot | WASH PM | SI | sit.watsan@solidarites_myanmar.org | 09420070354 |
| Maud Jimenez | WASH Head of Dept | ACF | washco@mm.missions-acf.org |  |
| Ewinur Machdar | WASH | UNICEF | ecmachdar@unicef.org |  |
| Sandra Eigenheer | Wathab engineer | ICRC | seigenheer@icrc.org |  |
| Damian Seal | WASH and infrastructure CO | DRC | damianseal@drcmm.org |  |
| Haymer | MIE | CDN | cdn.health.education.sittwee@gmail.com | 09421732845 |
| Lei Yee Nway | WASH consultant | UNICEF | leiyeenway.myanmar@gmail.com | 09450015864 |
| Lae Yee Win | WASH consultant | UNICEF | pannlaephya7@gmail.com | 09254820143 |
| Kap Zo Lian | WASH consultant | UNICEF | kapsolian@gmail.com | 09253566833 |
| Klun Phyu | WASH consultant | UNICEF | zaygar.khinphyu@gmail.com | 09421757458 |
| Kyaw Thet | WASH | UNICEF | kthet@unicef.org | 0920721457 |
| Vanda Lengkong | Interim HPUM | PLAN | vanda.lengkong@plan-international.org | 09263912041 |
| Theew Si Htin Zeur | Coordinator | SCI | theesithin.zeur@savethechildren.org | 0973199862 |
| Manish Mehta | Humanitarian Coordinator | Oxfam | mamehta@oxfam.org.uk | 09254413987 |
| Federica Cinerelli | Program Manager | CDN/ZOA | rakhine.pgm@cdnmyanmar.org |  |

Apologies: Relief International

Agenda:

| Sr. | Topic | Who |
| --- | --- | --- |
|  | Pond cleaning update | All |
|  | Village level flood response, 3W | All |
|  | Flood response/sanitation in camps | All |
|  | Village level household sanitation | All |
|  | Returnees/relocation update | All |
|  | Information management – 4W | All |
|  | AOB | All |

Minutes:

| Topic 1: Pond cleaning, flood response |
| --- |
| Summary of discussion | Pond cleaning activities will be finalised by 15 September, as agreed upon. District DRD requests that agencies finish in Mrauk U district by 10 September. ACF will continue with pond cleaning using fishing nets as “in-situ” filtration, without removing any water. Agencies are considering what to do with pumps once pond cleaning has been finished. More than 100 pumps are available. Agencies to check with donors/logistics/mode of provision (donation only, support for operations and maintenance, training in operation etc)/what to keep (eg just suction hose, pump and suction hose) etc and then agree upon a small number of standardised options across the cluster. Options may include: Donation to DRD Provision/donation to on-going livelihood/agriculture projects Donation to village level committees Donation to villages that were not able to dewater this season, for later dewatering at their discretion Keep in store for future flood events and donate at the end of the year Keep in store for dry-season proofing Cash for work: WASH cluster has agreed that cash for work will NOT be used for emergency flood response pond cleaning activities. It will continue to be used, however, for pond upgrading, fencing etc. Cluster to commence planning for dry season, particularly in light of dewatering that has been undertaken. Township level meetings have been undertaken to coordinate Komen WASH response for Minbya, Mrauk U, Myebon, Ann, Rathedung, Ponnagyun, Pauktaw, Kyauktaw etc. Bilateral discussions are ongoing with agencies responding in Maungdaw and Buthidaung |
| Action Points | Request to agencies to continue to submit 3W for flood response to cluster. Request to agencies to discuss with donors the impact of dewatering on water supplies in the next dry season and request funds for dry-season proofing projects. Future agenda items: dry season preparedness; contingency planning/materials to be stored for future flood event; lessons learned from flood response. Outstanding request: guidelines on cash for work, standardisation of skilled and unskilled payments, incentive payments etc. |
| Topic 2: Village level Komen response (excluding pond cleaning/dewatering) |
| Summary of discussion | WASH in TLS: - PLAN has started reconstruction of schools and will incorporate WASH facilities. Lack of clarity in village names. Request to Education cluster for P-codes. WASH cluster will collaborate will Education sector to ensure that overlaps don’t occur with Education actors who are undertaking rehab/repair/construction of existing school/TLS facilities. Care needs to be taken to focus activities on Komen damage only, not works that existed prior to the floods/winds. Attention is to be given to ensure that the TLS has the capacity for O&M of any new WASH facilities. WASH in health centres: MSF and ICRC have already undertaken some minor repair works and continue with their ongoing O&M activities. Request from Health cluster for list of health clinics with WASH needs. WHO expects to provide a list of 285 damaged health facilities. WASH cluster will distribute in conjunction with re-distribution of Education TLS list. WASH cluster will collaborate will Health sector to ensure that overlaps don’t occur between Health actors who are undertaking rehab/repair/construction of existing health centre facilities. Care needs to be taken to focus activities of Komen damage only, not works that existed prior to the floods/winds. Attention is to be given to ensure that the health centre has the capacity for O&M of any new WASH facilities. |
| Action Points | Request to Education sector for P-codes for TLSs that need WASH repairs. WASH cluster to coordinate with Education sector to confirm what repairs are already being undertaken by Education agencies. Request from Health cluster for list of health clinics with WASH needs. WASH cluster to coordinate with Health cluster to confirm what repairs are already being undertaken by Health agencies. |
| Topic 3: Komen response in camps |
| Summary of discussion | - Most agencies note that damage in camps was caused by winds, not flood waters. - DRC, Oxfam, CDN continue to replace/repair damaged latrines as part of the existing maintenance program. - SI has replaced nearly 60 latrines in conjunction with shelter rehabilitation. Some latrines are still flooded, so desludging is ineffective. - Obtaining permission for additional latrines in camps can be difficult due to landownership issues. Some agencies have found that allocating one latrine between two or three shelter rooms (that is, one “family latrine with lock” between maybe four families) increases ownership, resulting in improved maintenance/cleaning. - GBV coordinator from IRC has offered to facilitate gender mainstreaming for WASH in camps; it is requested that GBV and WASH guidelines to be incorporated into WASH activities. |
| Action Points | - IRC GBV coordinator to present for 10 – 20 minutes at next WASH cluster meeting. - Hygiene TWG to be reconvened to finalise outstanding activities in a month, led by SCI. - TWG for latrine design in camps to be held ASAP. Agencies to submit superstructure design to google group for sharing/consolidation at TWG. |
| Topic 4: Relocations |
| Summary of discussion | WASH agencies are requesting clarifications or a “technical working group” (or some coordination mechanism) for returns/relocations. Queries include if agencies should support “relocations result in camp-like settings but with people in individual houses”? What is the mode of relocation (such as cash grant only/cash grant plus materials/materials plus contractors)? Who will support householders with technical support (many HH have not previously used HH latrines, so don’t know technical aspects)? What is the approach for villages where there is not enough space for latrines (consider community level latrines?)? Who will operate and maintain, renew latrines? What are the coordination mechanisms with TAs, as the responsible authority? Who will build latrines for people who are still in villages? |
| Action Points | - WASH cluster to clarify WASH requirements for returns/relocations. - WASH cluster to request the timing, numbers, locations of returns/relocations |
| Topic 8: Authorisation for WASH activities by township authorities |
| Summary of discussion | Only ACF agency continues to have issues with authorisation to extend existing activities into flood response. |
| Action Points | ACF to notify WASH cluster if additional support is required with authorities. |
| Topic 9: AOB |
| Summary of discussion | - Request for future agenda item: inadequacy/lack of safety of drainage of drainage in camps during floods |
| Action Points | Item to be added to future agenda. |

Next meeting: Friday, 18 September 2015, 10:00 – 12:00, UNICEF Sittwe