Rakhine WASH Cluster

Agenda for Rakhine WASH Cluster Meeting

Date:   	07/04/2017

Venue: 	UNICEF office

Time: 	10:00h ~ 11:15h

Duration: 	1hr 15 minutes

Chair:		Rakhine WASH Cluster

Attendees:

| No | Name | Designation | Organization | Email | Phone |
| --- | --- | --- | --- | --- | --- |
| 1 | Stephanie tam | WASH Coordinator | DRC | Stephanie.tam@drcmm.org | 09 451978852 |
| 2 | Lae Yee Win | WO | UNICEF | laewin@unicef.org | 09 254820143 |
| 3 | Kris Cahyanto | WASH Specialist | UNICEF/ Cluster | bkcahyanto@unicef.org | 09 251643911 |
| 4 | Melvin Tebbutt | HARP | HARP | melvin.tebbutt@harpfacility.org | 09762492716 |
| 5 | Nicolas Guillavd | Consortium Mannager | SCI | NICOLAS.GUILLAUD@savethechildren.org | 09 43049814 |
| 6 | Nyi Nyi Thit | WASH Officer | UNICEF | nthit@unicef.org | 09421733834 |
| 7 | Toe Toe Aung | PHEO | Oxfam | Toetoeaung221175@gmail.com | 09 254896432 |
| 8 | Maung Aye Yin | PHPO | Oxfam | ayin@oxfam.org.uk | 09 421768254 |
| 9 | Thaw Si Htin Zaw | WASH PM | SCI | Thawsihtin.zaw@savethechildren.org | 09 456250150 |
| 10 | Zaw Min Tun | WASH Team Leader | CDN | Washtl.sittwe@cdnmyanmar.org | 09 798230379 |
| 11 | Ewan Chainey | WASH Cluster Coordinator | Global WASHCluster | ebchainey@unicef.org | 09 423404899 |

Agenda:

| Sr. | Topic | Time | Who |
| --- | --- | --- | --- |
| 1. | Self-Introduction | 5 min | All Participants |
| 2. | Review of action point from previous meeting | 5 min | Ewan |
| 3. | 4Ws Review | 10 min | HARP+ All Participants |
| 4. | WASH Emergency Preparedness Plan for 2017 | 10 min | All Participants |
| 5. | UNHCR WASH Assessment | 10 min | Ewan |
| 6. | Labour Incentive rates | 10 min | HARP+ All Participants |
| 7. | Update/ input on WASH Situation Analysis | 10 min | Kris |
| 8 | AWD Update | 5 min | Ewan |
| 9 | AOB | 5 min | All Participants |

Minutes:

| Topic 1: Review action points from previous meeting minutes |
| --- |
| Summary of discussion | Revision on WASH 4Ws will be made to accommodate current WASH services in the camp and host villages/ surrounding areas. HHs & Population Data will be provided by CMAs New WASH Cluster Coordinator will follow up on 4 W update Current 4 Ws will be used for first Quarter 2017 and next quarter will be used with updated format Indicator will be calculated with Sphere Standard WASH Cluster will collect the data from WASH Agencies. ICRC support WASH facilities for Ah Htet Nan Yar Camp – possibility/Kris WASH Cluster will share water shortages villages and information about water shortage – after April WASH Cluster will follow closely on this development for NRS with RCO NFI Cluster coordinator will coordinate in future to avoid duplication between NFI Cluster and WASH Cluster in WASH related items distribution - Richard written an email to that end to all concerned. |
| Action plan | Presentation on HK Kits Strategy will be present in next WCM by DRC and will share HHs Survey, discussion guidelines and SCI will translate – 20 minute presentation on 28/04/17. New mechanism for NRS response from UNHCR will be shared and UNHCR will focus on only Humanitarian Response NRS issues for emergency response and coordination will be led by RC Office DRD will share water sacristy data for rural areas to WASH Cluster with their plan - received Guideline for water trucking draft developed - Done Ewan, Kris and one national staff will go NRS on 11 – 12 April for Coordination and WASH response - Done |
| Topic 2: 4Ws Review |
| Summary of discussion | DIFID Consortium started on the construction of WASH facilities data analyze and facing on planning and access review on the construction of WASH facilities. It’s good to access of needs and based on Funding requirement and what want to do. Analysis is basic review infrastructure Data on camps, villages and host communities is very complicated in current situation. Existing WASH data monitoring is based on how many them are functioning/ non functioning Population figure for each camp is collected by WASH Consortium Agencies last year Calculated on targets and infrastructure assuming in the camps; for Sanitation is calculated based on HHs 1 latrine/ 4 HHs and for Water 20 litres/ person/ day. Assuming on borehole using for calculation is 30 litres/person/ day and timing is 30 l/ person/8 hrs. Criteria of desludging is trigger monitoring system updated and different of functioning latrines, desludging process and using of pressure pumps and twice per year for desludging Water Quality Testing is basically coverage |
| Action Plan | HARP will make presentation to NWCC meeting on May 5th Way forward is to incorporate and harmonize with 4ws over the next quarter Specific to Sittwe and Consortium camps: Rehabilitation of existing latrines is ongoing. 200 Latrines and a few numbers of water points will be constructed provisionally by September 2017. WASH facilities will be repaired in gap area within transition period. |
| Topic 3: WASH Emergency Preparedness Plan for 2017 |
| Summary of discussion | WASH Agencies need to share their stock list and Contingency plan for 2017 – ongoing/not finalized Last ICCG Meeting, discussed on WASH Agency focal point for Township level and to prepare for Coordination Mechanism and Capacity Building with Local authorities and CBOs - ongoing |
| Action Plan | Action points for next cluster Meeting for coordination mechanism – ICCG held – WASH Cluster forwarded argument that EPREP should be government led - ongoing WASH Cluster will share Emergency stock, contact list and ERP plan - Done |
| Topic 4: UNHCR WASH Assessment |
| Summary of discussion | Ewan met with Protection and Cluster and will follow up action points and wash agencies will support for information sharing and cross check |
| Action Plan | Ewan will send the WASH Protection Assessment format and WASH Cluster agencies will feedback of complain mechanism - Done |
| Topic 5: Labour Incentive rates |
| Summary Discussion | Shared to UNOCHA and HARP updated modifying with EXCEL sheet |
| Action Points | National WASH Cluster will be present in NWC for O & M and compare with other clusters/sectors Rakhine WASH Cluster to have meeting/TWG to finalize a standard for Labour Incentive rates – specific to the WASH actors |
| Topic 6: Update/ input on WASH Situation Analysis |
| Summary Discussion | Kris shared WASH Situation Analysis report and base line data sheet to Rakhine WASH Cluster two weeks ago |
| Action Points | WASH partners need to feedback and input for that - ongoing |
| Topic 7: AWD Update |
| Summary Discussion | WASH Cluster to updated AWD plan with table of key activities – Done /and forwarded to Health |
| Action Points | Health Cluster will finalize for validation – by First week May |
| Topic 8: AOB |
| Summary Discussion | JIPS Update Water Shortage and Distribution Plan for coming months – urgent need Next WASH Cluster Meeting will be held on 28 April 2017. |
| Action Points | DRC JIPS will share Camps update for Sittwe Camps – will be finalized at end of May UNICEF and WASH Cluster will coordinate with DRD – Done |