Rakhine WASH Cluster

MoM Rakhine WASH Cluster Meeting

Date:   	10/06/2016

Venue: UNICEF

Time: 	10.00 – 11.30

Chair: 	James Robertson, WASH Specialist & Rakhine WASH cluster coordinator

Attendees:

| No | Name | Designation | Organization | Email Address | Contact Phone Number |
| --- | --- | --- | --- | --- | --- |
| 1 | Mg Thein Shwe | Team Leader | ACF | mgtheinshwe@gmail.com | 09-421710339 |
| 2 | Zaw Myo Wai | Sr. WASH Officer | IRC | Zawmyo.Wai@resue.org | 09-4505427282 |
| 3 | Thaw Si Htin Zaw | Acting Manager | SCI | thawsihtin.zaw@savethechildren.org | 09-263941435 |
| 4 | Han Min Htet | WASH Coordinator | SCI | hanmin.htet@savethe children.org | 09-440224018 |
| 5 | Stephanie Tam | WASH Coordinator | DRC | stephanie.tam@drcmm.org | 09-451978852 |
| 6 | John KNIGHT | PHE Coordinator | Oxfam | jknight1@oxfam.org.uk | 09-420016876 |
| 7 | James ROBERTSON | WASH Specialist | UNICEF | jrobertson@unicef.org | 09-972721599 |
| 8 | Kirs Cahyanto | WASH Specialist | UNICEF | bkchyanto@unicef.org | +959251164394 |
| 9 | Ann REJAER | Head of Office | RI | ann.reiner@ri.org |  |
| 10 | Adrien PETTPER | Water Manager | SI |  |  |
| 11 | Soe Myint | PMA | SI | sit.pm.assist@solidarities.myanmar.org | 09-420760312 |
| 12 | Sandra Eigenheer | Wathab Engineer | ICRC | seigenheer@icrc.org | 09-420281442 |
| 13 | Ye Htut | WASH Project Manager | CDN | yehtoot6@gmail.com | 09-5408747 |
| 14 | Toe Toe Aung | PHEO | Oxfam | toetoeaung221175@gmail.com | 09-254896432 |
| 15 | Thaw Tar Lapypelyn | HPO | Plan | Thawtar.lapyae@plan-international.org | 09-261885252 |
| 16 | Nyi Nyi Thit | WASH Officer | UNICEF | nthit@unicef.org | 09-421733834 |
| 17 | Kyaw Thet | WASH Officer | UNICEF | kthet@unicef.org |  |
| 18 | Lae Yee Win | WASH Officer | UNICEF | laewin@unicef.org | 09-254820143 |
| 19 | Lae Yee Nway | WASH Officer | UNICEF | lnway@unicef.org | 09-450015864 |

Agenda:

| Sr. | Topic | Who |
| --- | --- | --- |
| 1 | Self-Introduction | All Participants |
| 2 | Agenda introduction by Wash Cluster Coordinator | Myanmar WASH Cluster Coordinator |
| 3 | Update of activities per agency | All Participants |
| 4 | IDP figures & Activities in Camps (Armed Conflict) | All Participants |
| 5 | 4W/ Monitoring re-design process | Myanmar WASH Cluster Coordinator |
| 6 | Link with new Minister and WASH Cluster | All |
| 7 | AWD | All |
| 8 | AOB |  |

Introduction

The WASH Cluster meeting was conducted at UNICEF and chaired by the National WASH Cluster coordinator (OIC).  There are new WASH staffs from 4 agencies : SI, Oxfam, DRC, and UNICEF. WASH cluster welcomes new WASH focal points from these agencies.

Minutes:

| Topic 1: Action points from update of activities by Agency |
| --- |
| Update situation in targeted areas | SI: SI reported some challenges working in the latrine construction programme in their service area. CMC is willing to work, only if there is contract available for CMC. Negotiation with CMC is being conducted. Construction of Latrine activities is ongoing in Dar Pai Camp. ICRC: Ceramic water filter distribution, including rainwater-harvesting material (Tarpaulin, bamboo, rope and bucket), 712 packages of RWH kits were distributed this period in two villages in Mrauk U Township. During the last distribution fro the Komen response, 11.000 packages of RWH kits were distributed. 200 x 20 litres water bottles/ day/ Household are distributed until 12th of June in Say Taung village for the new IDPs. CDN: International WASH evaluator is coming to Rakhine-Sittwe, TOR will be shared to the cluster. Regular Hygiene promotion sessions are conducted and new latrines will be constructed in Kaung Doke Khar Camp and Ohn Taw Chay Camp in Sittwe Township. Plan: WASH project has finished on 31st of May, 2016 in Minbya township and next proposal is not approved yet and in process. IRC: Water Distribution with temporary tanks and 5008 liters of purification water bottles were distributed in IDP Camps in Rathedaung Townships. SCI: Installation of new battery for solar lamp systems is being developed in 5 Camps. Assessment on the utilization of ceramic water filters was done; distribution of CWFs and Clay filters and spare parts is planned after the assessment. Desludging process is challenging in the rainy season and planning to construct new extra digging pits. DRC: Few activities on hygiene promotion, and hygiene kits distribution. ACF: Rainwater harvesting ponds rehabilitation done in the past few weeks. WASH project has finished on 31st of May, 2016 in Minbya township and urban areas and 31 bore holes will be constructed in Sittwe and Minbya areas. 1 Spring with piping system will be constructed in Minbya downtown. Oxfam: CMC agreed not to continue the regular payment on latrine cleaning and will be replaced by community latrine cleaning mechanism. Desludging is done according to the agency request; this activity is now slowing down due to the rainy season. Ceramic Water Filters distribution in Say Tha Mar Gyi Camp and Latrine Management Trainings are conducted. UNICEF: There will be official meeting between the government at the state and national level on 16 June 2016. All WASH partners are requested to share key WASH messages for the WASH stakeholders, donors, and government officials both from national and state level. |
| Action points | WASH Cluster to share the simplify 4 Ws update to combine the data. |
| Topic 2: Action Points from IDP figures & Activities in Camps (Armed Conflict) |
| Situation in Camps | Due to the fighting between the Union Army and Arakan Army in Rakhine State; OCHA is calling for joint assessment missions in four townships. Approximately 2000 households are reluctant to go back to their village for safety reason. Cluster member that is working nearby the area is expected to participate in the assessment. |
| Action points | Coordination meeting between Unicef, OCHA and Oxfam on the joint assessment mission in 4 townships. |
| Topic 3: Action Points from 4W/ Monitoring re-design process |
| Update from TWG/OCHA-led process | WASH reporting mechanism on 4Ws. The new 4Ws indicators will be simplified into approximately 20 keys WASH indicators on Water Supply, Sanitation, and Hygiene, simplification from more than the previously 50 indicators . Further inputs on these 20 key indicators are welcome. |
| Action points | For new regular WASH reporting mechanism, National WASH Cluster to share the draft of 4Ws indicators. The regular WASH update should include funding status and gap for WASH response. |
| Topic 4: Health and WASH coordination (AWD) |
|  | WASH Cluster will be finalized AWD from Technical Working Group. |
| Action points | a. SI & Oxfam will share the final AWD document. b. Close coordination between Health Cluster & WASH Cluster to monitor the trend on AWD during the rainy season period, |
| Topic 5: Advocacy/ Coordination Meetings with Governments |
| Feedback from meetings | Regular Coordination meetings with governments (union level, state level) for WASH Strategy and WASH related issues. And Rakhine State Development Work plan Workshop will be held on 16- 17 June 2016 with high level authorities and International organisations. |
| Action points | WASH cluster to share their input for the development of WASH situation in Rakhine State. UNICEF will do presentation on FRIDAY, 17.6.2016. UNICEF to share the rural WASH strategy for Myanmar, which was agreed by 3 ministries at the national level. |
| Topic 6: AOB |
|  | Next meeting: Friday 24 June, 2016, 10:00 – 12:00, to be confirmed. |