WASH Cluster Myanmar

Minutes of National WASH Cluster Meeting

Date: Tursday 13th of August 2015    Venue: UNICEF Meeting hall

Time: 10 am     Duration: 1 h30 expected

Chair:	Olivier Le Guillou, WASH Cluster Coordinator

| Sr. | Topic | Time | Who |
| --- | --- | --- | --- |
| 1 | Self-Introduction | 5 min | All Participants |
| 2 | Agenda introduction | 5 min | NWCC |
| 3 | Flooding situation update and Wash coverage/gaps | 15 | NWCC + feed back Partners |
| 4 | Information management | 15 min | MIMU + NWCC |
| 5 | Overall strategic Wash response definition | 20 minutes | NWCC |
| 6 | CERF funding | 10 minutes | UNICEF |
| 7 | Coordination mechanism | 5 minutes | NWCC |
| 9 | AOB | 5 Minutes | All participant |

Minute:

| Topic 1: Self-Introduction |
| --- |
| Summary of discussions | 32 participants from 25 agencies introduced themselves. |
| Action Points | Good attendance, showing high interest and concern for the flooding situation |
| Topic 2 : Agenda introduction by National Wash Cluster Coordinator |
| Summary of discussions | Meeting focalizing on Flood, situation update and strategic orientation to be taken |
| Topic 3 : Flooding situation and wash response |
| Summary of discussion | Situation: See attached power point for figures (1.1 million affected persons) presented during the meeting Ministry of Social Welfare, Relief and Resettlement' s Response by State/Region, associated to OCHA sitrep, and EOC supported with MIMU MIRA assessment on going The number of affected population has drastically increased in a week. However the definition of Affected population is broad, and do not reflect yet the population in needs The same 5 States (Rakhine, Sagain, Chin, Magway and Ayeyarwadi) remain at concern Wash needs are obvious, and in most feedback received from evaluation mentioned as a second priority after food assistance Data on Chin state remains low and do not reflect the reality: MIRA on-going over there MIRA is on-going also in Ayerwaddi with UNICEF wash participation Concern has been express about new emergency Wash actors stepping in Rakhine, where already, for protractile emergency, the wash network is strong, while other state remain under served. Also in Rakhine itself a lot of attention is given to the North, while Ann Township is at concern. It was also strongly stated that the focal wash NGO per location (camps and communal conflict affected population/surrounding communities) should not be disturbed by the new wash incomers, welcome to complement the coverage of population affected by the flooding. Kalae remain at concern looking at the distribution of beneficiary per township, being so far the higher numbers The response is still on assessment phase, associated with NFI distribution. Main responder at that stage is the government and MRCS. Rakhine has been more reactive due to the pre-existing Wash emergency network The civil society response in evacuation center seems to be strong and covering first day needs Kachin, where location was flooding slightly before the other state, seems to be close to the normal now It is strongly expected that in the coming days the response become more consequent and ideally can switch rapidly to rehabilitation in an early recovery perspective At that stage it is difficult to report on what is achieved, while 3W tools are under consolidation between the actors Challenge: The contamination of pond in Rakhine is a high concern, while the rehabilitation will require to dewater those structure on which the population rely during 6 months of dry season. Meaning that the rehabilitation should take place as soon as possible to allow their feeling before the end of the raining season Emergency water supply will need to be set for short term in some location with logistic constrains The supply of purifying tablet is to be speed up Launching ASAP rehabilitation phase Information management and analysis of the situation Get a clearer picture of Governmental plan |
| Action Points | MIRA to be compile (OCHA) 3W to be completed for Monday 17th the latest Liaise with DRD on response plan: Meeting in NPT the 18th |
| Topic 4 : Information management |
| Summary of discussions | At that stage many information are received but on a destructed way, receiving different templates, from micro to macro analysis, difficult to explore and compare. The 3W has been launch in order to simplify the basic necessary information, to be progressively upgraded with details, in order first at all to look at geographical coverage per NGO, and in a next step reporting of action taken. Mimu presented their product and strong support that can be provided (maps, liaising data with authorities, 3W, printing facility, Rakhine Sitrep expected Friday Wash cluster is communication and sharing information through 'myanmar_wash_sector@googlegroups.com'. Contact persons is Thein Tun Hlaing tthlaing@unicef.org |
| Action Points | Following report release Evaluate possibility to replicate in Kachin Continuously advocate for the importance to keep that cross cutting issue as a major concern |
| Topic 5 : Coordination |
| Summary of discussion | Regular Wash cluster meeting hold in Yangon and Rakhine once a week Rakhine response should coordinated with past intervention Wash Kachin Sub-cluster will be dedicated in the field during 2 week to support Chin and Sagain situation analysis and response definition, and coordination with authorities Didier Boissavi dboissavi@unicef.org HCT and ICCG meeting regular, update will be shared Will be important before end of august to liaise back with previous problematic as Kachin state events (opening of Kokang, and arm clashed in North Kachin) |
| Action Point | Wash cluster situation analysis to increase |
| Topic 6 : Strategic approach |
| Summary of Discussions | A wash cluster guidance has been produce and shared, with the following key elements: Governmental led response 500,000 people targeted in 5 district (prioritization?) 6 months Early recovery priority not to stuck in emergency response Resilience of population to take in consideration DRR and do no harm 3 phases, relief, early recovery and rehabilitation Sanitation potential limitation Modalities: Cash approach to be considered where possible and relevant in early recovery phase Sanitation is at concern to fine the good balance in a do no harm perspective, not to provide “too much’ at household level which can jeopardize the future of development is the targeted location as CLTS Wash cluster provide guidance for Pond cleaning and use of purification tablets (which should not be dump to beneficiary but distributed with appropriate explanation) |
| Action point | Document to be validated by Friday 14th, all comment welcome in the mean time |
| Topic 7: CERF UNICEF funding |
| Summary of Discussions | UNICEF briefly presented the emergency CERF funding available for the Wash sector 2.1 MUSD For flooding affected population Which can be used to support directly government, direct response with private sectors and project with NGO Call of proposition for NGO will be send Friday 14th covering 4 month max response for relief response and early recovery Selection process should be fast, in a week time to be engage hopefully |
| Action point | Call of proposition to be launched by UNICEF Selection and launching implementation ASAP |
| Topic 10 : AOB |
| Summary of findings | Next wash cluster date to be defined |
| Attachement: |