**INTER-AGENCY MULTISECTORAL RAPID ASSESSMENT PLAN**

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **State** | **Townships** | **Team leader** | **Contact** | **Team members** | **Tentative Location** | **Tentative Date** | **Comments** |
| **Org** | **Staff Name** |
| **Sagaing** (aprox 4 teams made of 3/4 members)  | Kale, Kyunhla, Kawlin, Kanbalu | OCHA | Moe Aung, Head Bhamo SO | 09-8602829,moe.aung.13@gmail.com | UNICEF/Khaing Khaing ShweWHO/Dr Tin SweWHO/Dr Nyunt SeinWHO/Dr Aung Ko Ko HeinWHO/ Chaw Su HlaingUNFPA/Dr Win AungUNDP/Kyaw Swar LwinUNDP/Kyi Zaw LwinUNDP/Aung Tin MoeWV/Ngum Za LiamUNICEF/Tin HtutUNICEF/Mra ThuzarUNICEF/Shwe Hla OoUNICEF/Khin Mar WinMSI/KMSS/Ayaryone Oo/MRCS/Zomi Youth Association | Kale  | 10 Aug | Meeting w authorities postponed for tomorrow 11Aug. Teams already started assessments (4 teams) in Kale and planned to be finalized by tomorrow. Access to affected villages challenging with roads covered with mud and sediments. Some creeks divert their waterway and local authorities and community are constructing temporary bamboo bridges to cross newly appeared waterways. Water receded in almost all flooded villages. Villages are also covered with muds and sediments (at some villages 3 to 4 feet high) Some people from those villages are still staying in evac centers in town and villages. Some are constructing makeshift bamboo huts along motor roads. |
| Kale  | 9/10 Aug | Assessments ongoing |
| Mandalay  | 12 Aug | Team to arrive in Mandalay, mission preparations |
| Kawlin, Kanbalu, Kyunhla | 13/15 Aug | Assessments in these locations |
| **Magway** (TBC) | Saytottata, Pyint Phyu | UNDP | Aung Linn,Area office coordinator | 095280810,Aung.linn@undp.org | UNICEF/Thida SeineWHO/Dr Kyaw Min TheinWHO/Dr Kyi Thar LoonSC/Swe Linn MaungWV/Ngum Za LiamWFP/Nay WinUNDP/Hla Aung MyintUNDP/Win NaingUNDP/Chaw Su KhinUNDP/Yan Naing TunUNDP/Khin Maung LwinUNFPA/Dr Aung Thu TunNAG/Wai Lin Cho | Magway | 10 Aug | Team members’ arrival, briefing, meeting authorities and stakeholders. Proposed assessments in Sidoktaya and Pwintbyu but needed to be revised as there are townships with higher number of population affected.  |
| Sidoktaya | 11/15 Aug |  |
| Pyint Phyu | 11/15 Aug |  |
| **Chin** (TBC) | Hakha | UNICEF | Mohammad Badrul Hassan,Chief Hakha FO | 09-250344964mbhassan@unicef.org | WHO/Dr Wai Yan Yee MonWHO/Dr Aung Ye PhoneUNICEF/Biak Sung UNICEF/Myo Min Lwin UNDP/ Aung PaingUNFPA/Dr Tay Zar SoeWV/ Vum Liam ThawngMSI/Sanda LinMSI/Ah Yon OoUNHCR/ Hau Lam VungCPTC/Tluang CeuCARD/ Daw Ngai ManCAD/Thang Cin LianGreen/ Anthony Cung MangKMSS/James Ngun HreUNICEF/Piang Sung Mung UNICEF/Kap Za Lyan UNICEF/Hein Latt UNICEF/Ngin Tung Nung ADRA/KMSS/Ca HuSC/Phone Thant | Hakha | 10 Aug | Meeting called by Chin government. CM asked for assessments in **ALL** townships and further discussions from 11 Aug. With current staff for assessment, capacity to cover besides Hakha, Tonzang, Tedim and Matupi. Need to discuss with INGO in Paletwa (ACF + IRC) feasibility of MIRA assessments as it is one of the most affected + inaccessible townships |
|  |  |  |
| **Ayeyarwaddy** | Nyaungdon, Zalun, Danuphyu, Hinthada | WFP | Kyaw Kyaw Lwin | 09788030715 | WFP/UNICEF/Kyaw Lwin Latt, UNICEF/Theingi SoeUNICEF/Aye Aye KyuUNICEF/Htoot Min |  | 7 to 10/11 Aug |  |
| **Bago** | Moe Nyo | WFP | Ma Chan |  | UNICEF/Kyaw Win OoUNICEF/Myo Min Soe UNFPA/Dr Seng Aung Sein Myint |  | 9 to 11/12 Aug |  |