REQUEST FOR PROPOSAL – RFP

Services

Ref: YGN/ED/ESPIG/RFP/2025/03

(Please quote this UNESCO reference in all correspondence)

Date 11 April 2025

Dear Sir/Madam,

We invite you to submit a proposal to support children and youth in Myanmar through the development of online content that focus on vocational skill development. The objective is to reach conflict-affected, vulnerable, disadvantaged, and out-of-school girls and boys, providing them with safe, inclusive, and high-quality learning opportunities through digital learning experiences. The project timeline will span from July 2025 to February 2026, aligning with the current solicitation document.

The Request for Proposal (RFP) consists of this cover page and the following Annexes:

Annex I	Instructions to Offerors

Annex II	General Conditions of Contract

Annex III	Terms of Reference (TOR)

Annex IV	Proposal Submission Form

Annex V 	Price Schedule Form

Annex VI	Vendor Information Form

Your electronic offer comprising of (1) technical proposal and (2) financial proposal should be sent through two separate emails, no later than 2 May 2025 16:00 hours, Yangon, Myanmar time, to below email address without any copy to any other e-mail addresses (File size maximum 10 MB). Offers addressed at any other e-mail accounts will be disqualified:

- Technical offer should be sent to the following email, with the mention “Technical Proposal - YGN/ED/ESPIG/RFP/2025/03” in subject.

- Financial offer should be sent to the following email, with the mention “Financial Proposal - YGN/ED/ESPIG/RFP/2024/03” in subject.

Financial Proposal MUST be password protected.

UNESCO Regional Office in Bangkok

Email address: procurement.bgk@unesco.org

Reference: YGN/ED/ESPIG/RFP/2025/03

Closing Date and Time: 2 May 2025 – 16:00 (Yangon time)

This letter is not to be construed in any way as an offer to contract with your firm/institution. Your proposal could, however, form the basis for a contract between your organization and UNESCO.

You are requested to acknowledge the receipt of this letter and to indicate whether or not you will be submitting a proposal. For this purpose, and for any requests for clarification, please contact at procurement.bgk@unesco.org.

For and on behalf of UNESCO

Ichiro Miyazawa

Head of Yangon Project Office

#### ANNEX I – Instructions to Offerors

These instructions contain general guidelines and instructions on the preparation, clarification, and submission of Proposals.

A. INTRODUCTION

1. General

The purpose of this Request for Proposal (RFP) is to invite Sealed Proposals for professional services to be provided to the United Nations Educational, Scientific and Cultural Organization - UNESCO.

2. Eligible bidders

Bidders should not be associated, or have been associated in the past, directly or indirectly, with a firm or any of its affiliates which have been engaged by UNESCO to provide these services for the preparation of the Terms of Reference, and other documents to be used for the procurement of services to be purchased under this Request for Proposal.

This bid is open to all national and international organizations who are legally constituted, can provide the requested services.

Bidders are ineligible if at the time of submission of the offer:

(a) The bidder is on the exclusion list published on the global portal for suppliers of the United Nations Organization, (http://www.ungm.org) due to fraudulent activities.

(b) The name of the bidder appears on the Consolidated United Nations Security Council Sanctions List which includes all individuals and entities subject to sanctions measures imposed by the Security Council.

(c)The bidder is excluded by the World Bank Group.

3. Fraud and corruption

UNESCO requires that bidders, contractors and their subcontractors adhere to the highest standard of moral and ethical conduct during the procurement and execution of UNESCO contracts and do not engage in corrupt, fraudulent, collusive, coercive or obstructive practices.

For the purpose of this provision such practices are collectively referred to as “fraud and corruption”:

- “Corrupt practice” is the offering, giving, receiving or soliciting, directly or indirectly, an undue advantage, in order that the person receiving the advantage, or a third person, act or refrain from acting in the exercise of their official duties, or abuse their real or supposed influence;

- “Fraudulent practice” is a knowing misrepresentation of the truth or concealment of a material fact aiming at misleading another party in view of obtaining a financial or other benefit or avoiding an obligation, or in view of having another party act to their detriment ;

- “Collusive practice” means an arrangement between two or more parties designed to achieve an improper purpose, including influencing improperly the actions of another party ;

- “Coercive practice” means impairing or harming, or threatening to impair or harm, directly or indirectly, any party or the property of the party to influence improperly the actions of a party.

- “Obstructive practice” means acts intended to materially impede the exercise of UNESCO’s contractual rights of audit, investigation and access to information, including destruction, falsification, alteration or concealment of evidence material to a UNESCO investigation into allegations of fraud and corruption.

- “Unethical practice” means conduct or behaviour that is contrary to Staff or Supplier codes of conduct, such as those relating to conflict of interest, gifts, hospitality, postemployment provisions, abuse of authority and harassment.

UNESCO expects that all suppliers who wish to do business with UNESCO will embrace the United Nations Supplier Code of Conduct

UN Agencies have adopted a zero-tolerance policy on gifts and therefore, it is of overriding importance that UNESCO staff should not be placed in a position where their actions may constitute or could be reasonably perceived as reflecting favourable treatment of an individual or entity by accepting offers of gifts, hospitality or other similar favours. Vendors are therefore requested not to send or offer gifts or hospitality to UNESCO personnel.

UNESCO will:

- Reject a proposal to award a contract if it determines that a vendor recommended for award has engaged in fraud and corruption in competing for the contract in question.

- Cancel or terminate a contract if it determines that a vendor has engaged in fraud and corruption in competing for or in executing a UNESCO contract.

- Declare a vendor ineligible, either indefinitely or for a stated period of time, to become a UN registered vendor if it at any time determines that the vendor has engaged in fraud and corruption in competing for or in executing a UNESCO contract.

Any concern or evidence that corruption or fraud may have occurred or is occurring related to a UNESCO contract shall be forwarded to the Office of Internal Oversight. Please refer to how-to-report-fraud-corruption-or-abuse.

4. Cost of Proposal

The Offeror shall bear all costs associated with the preparation and submission of the Proposal and UNESCO will in no case be responsible or liable for those costs, regardless of the conduct or outcome of the solicitation.

B. SOLICITATION DOCUMENTS

5. Contents of Solicitation Documents

Proposals must offer services for the total requirement. Proposals offering only part of the requirement will be rejected. The Offeror is expected to examine all corresponding instructions, forms, terms and specifications contained in the Solicitation Documents. Failure to comply with these documents will be at the Offeror’s risk and may affect the evaluation of the Proposal.

6. Clarification of Solicitation Documents

A prospective Offeror requiring any clarification of the Solicitation Documents may notify UNESCO in writing at the organisation’s mailing address or fax or email number indicated in the RFP. UNESCO will respond in writing to any request for clarification of the Solicitation Documents that it receives earlier than two weeks prior to the deadline for the submission of Proposals. Written copies of the organisation’s response (including an explanation of the query but without identifying the source of inquiry) may be sent to all prospective Offerors that have received the Solicitation Documents.

7. Amendments of Solicitation Documents

At any time prior to the deadline for submission of Proposals, UNESCO may, for any reason, whether at its own initiative or in response to a clarification requested by a prospective Offeror, modify the Solicitation Documents by amendment.

All prospective Offerors that have received the Solicitation Documents will be notified in writing of all amendments to the Solicitation Documents.

In order to afford prospective Offerors reasonable time in which to take the amendments into account in preparing their offers, UNESCO may, at its discretion, extend the deadline for the submission of Proposals.

C. PREPARATION OF PROPOSALS

The offers received must include information in sufficient scope and detail to allow UNESCO to consider whether the organization has the necessary capability, experience, expertise, financial strength and the required capacity to perform the services satisfactorily.

8. Language of the Proposal

The Proposals prepared by the Offeror and all correspondence and documents relating to the Proposal exchanged by the Offeror and UNESCO shall be written in English. Any printed literature furnished by the Offeror may be written in another language so long as accompanied by a translation of its pertinent passages in which case, for purposes of interpretation of the Proposal, the language as stated in the Solicitation Documents applies.

9. Documents Comprising the Proposal

The Proposal shall comprise the following components:

- Proposal submission form;

- Operational and technical part of the Proposal, including documentation to demonstrate that the Offeror meets all requirements;

- Price schedule, completed in accordance with clauses 10 &11;

10. Proposal Form - Presentation of the technical proposal

The Offeror shall structure the technical part of its Proposal as follows:

10.1. Description of the organization and its qualifications

(a) Management Structure

This Section should provide institutional orientation to include organization’s profile (year and country of incorporation – copy of certificate of incorporation), a brief description of present activities focusing on services related to the Proposal as well as an outline of recent experience on similar projects, including experience in the country.

The organization should describe the organizational unit(s) that will become responsible for the contract, and the general management approach towards a project of this kind. The Offeror should identify the person(s) representing the Offeror in any future dealing with UNESCO.

Offeror to provide supporting information as to organization’s technical reliability, financial and managerial capacity to perform the services.

(b) Resource Plan

This Section should fully explain the Offeror’s resources in terms of personnel and facilities necessary for the performance of the requirements, and any plans for their expansion. It should describe Offeror’s current capabilities/facilities and any plans for their expansion.

10.2. Proposed Approach, Methodology, Timing and Outputs

This section should demonstrate the Offeror’s responsiveness to the TOR and include detailed description of the manner in which the organization would respond to the TOR, addressing the requirements, as specified, point by point. You should include the number of person-working days in each specialization that you consider necessary to carry out all work required.

For assessment of your understanding of the requirements please include any assumptions as well as comments on the data, support services and facilities to be provided by the beneficiary as indicated in the Statement of Requirements/TOR, or as you may otherwise believe to be necessary.

10.3. Proposed Personnel

In this section, the offeror should reflect the project staffing including the work tasks to be assigned to each staff member as well as their qualifications with reference to practical experience relating to specialization area of the project for each proposed staff. The complete CV’s of proposed staff is to be submitted.

If applicable, this staffing proposal should be supported by an organigram illustrating the reporting lines, together with a description of such organization structure.

The technical part of the Proposal should not contain any pricing information whatsoever on the services offered. Pricing information shall be separated and only contained in the appropriate Price Schedule.

It is mandatory that the Offeror’s Proposal numbering system corresponds with the numbering system as provided in the TOR. All references to descriptive material and brochures should be included in the respective paragraph, though material/documents themselves may be provided as annexes to the Proposal/response.

11. Price Proposal

The Offeror shall indicate on an appropriate Price Schedule, an example of which is contained in the Price Schedule sheet, the prices of services it proposes to supply under the contract, if selected.

12. Proposal currencies

Your separate price envelop must contain an overall quotation in a single currency. All prices shall be quoted in US dollars.

13. Period of validity of proposals

Proposals shall remain valid for ninety (90) days after the date of Proposal submission prescribed by UNESCO, pursuant to the deadline clause. A Proposal valid for a shorter period may be rejected by UNESCO on the grounds that it is non-responsive.

14. Format and signing of proposals

The Offeror shall prepare two copies of the Proposal, clearly marking each “Original” and “Copy” as appropriate. In the event of any discrepancy between them, the original shall govern. The two copies of the Proposal shall be typed and shall be signed by the Offeror or a person or persons duly authorised. A Proposal shall contain no interlineations, erasures, or overwriting except, as necessary to correct errors made by the Offeror, in which case such corrections shall be initialled by the person or persons signing the Proposal.

15. Payment

In full consideration for the complete and satisfactory performance of the services of the contract, UNESCO shall effect payments to the Contractor within 30 days after receipt and acceptance of the invoices submitted by the contractor for services provided.

D. SUBMISSION OF PROPOSALS

16. Sealing and marking of proposals

Your electronic offer, comprising of (1) technical proposal and (2) financial proposal, should be sent through two separate emails no later than: 2 May 2025 16:00 hrs, Yangon  time, to below email address:

- Technical offer should be sent to the following email, with the mention “Technical Proposal - YGN/ED/ESPIG/RFP/2025/03” in subject: procurement.bgk@unesco.org

- Financial offer should be sent to the following email, with the mention “Financial Proposal - YGN/ED/ESPIG/RFP/2025/03” in subject: procurement.bgk@unesco.org

Note : Financial Proposal MUST be password protected. The authorized UNESCO officer will contact the bidders that pass the qualifying technical score for the password to open the Financial Proposal.

The email (including the files attached) should not exceed 10MB.

17. Deadline for submission of proposals

Proposals must be received on or before the date and time specified on the cover page of these Solicitation Documents.

UNESCO may, at its own discretion extend this deadline for the submission of Proposals by amending the solicitation documents in accordance with clause Amendments of Solicitation Documents.

18. Late Proposals

Any Proposal received by UNESCO after the deadline for submission of proposals, pursuant to clause Deadline for the submission of proposals, will be rejected.

19. Modification and withdrawal of Proposals

The Offeror may withdraw its Proposal after the Proposal’s submission, provided that written notice of the withdrawal is received by UNESCO prior to the deadline specified in the RFP. Proposals may not be modified or withdrawn after that time.

E. OPENING ANDEVALUATION OF PROPOSALS

20. Opening of proposals

UNESCO representatives will open all Proposals after the deadline for submissions and in accordance with the rules and regulations of the organization.

21. Clarification of proposals

To assist in the examination, evaluation and comparison of Proposals, UNESCO may at its discretion, ask the Offeror for clarification of its Proposal. The request for clarification and the response shall be in writing and no change in price or substance of the Proposal shall be sought, offered or permitted.

22. Preliminary examination

UNESCO will examine the Proposals to determine whether they are complete, whether any computational errors have been made, whether the documents have been properly signed, and whether the Proposals are generally in order.

Prior to the detailed evaluation, UNESCO will determine the substantial responsiveness of each Proposal to the Request for Proposals (RFP). For purposes of these Clauses, a substantially responsive Proposal is one, which conforms to all the terms and conditions of the RFP without material deviations. The determination of a Proposal’s responsiveness is based on the contents of the Proposal itself without recourse to extrinsic evidence.

A Proposal determined as not substantially responsive will be rejected by UNESCO.

23. Evaluation and comparison of proposals

A two-stage procedure will be used in evaluating the proposals, with evaluation of the technical component being completed prior to any price component being opened and compared. The Price Component will be opened only for submissions that passed the minimum score of 70 % of the total points obtainable for the technical evaluation.

The technical proposal is evaluated on the basis of its responsiveness to the Terms of Reference (TOR).

HIGHEST TOTAL SCORE OF WEIGHTED TEHCHNICAL AND FINANCIAL CRITERIA

The price proposal of all offerors, who have attained minimum 70 % score in the technical evaluation, will be compared. The contract will be awarded to the offeror that receives the highest score out of a pre-determined set of weighted technical and financial criteria as specified below.

Technical Proposal Evaluation Form

| Sample: Summary of Technical Proposal Evaluation Forms |  | Points Obtainable | Name of Firm / Institution |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | A | B | C |
| 1. | Expertise of Firm / Institution submitting Proposal | 200 |  |  |  |
| 2. | Proposed Work Plan and Approach | 300 |  |  |  |
| 3. | Personnel | 200 |  |  |  |
|  | Sub-total for Technical Evaluation | 700 |  |  |  |

Financial Proposal Evaluation Form

| Sample: Summary of Financial Proposal |  | Points Obtainable | Name of Firm / Institution |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | A | B | C |
|  | Financial Proposal | 300 |  |  |  |
|  | Sub-total for Financial Evaluation | 300 |  |  |  |

Evaluation of the price proposals (of all Offerors who have attained minimum 70 % score in the technical evaluation) will be based on the weight scoring method as follows:

- Financial proposals are opened and list of prices is prepared, where the lowest price is ranked as the first one (receiving highest amount of points) and the most expensive as the last one (receiving the least amount of points).

- Lowest price is given maximum points (e.g. 300), for other prices the points are assigned based on the following formula: [Amount of points = lowest price/other price * total points obtainable for financial proposal]

An example:

- Offeror A – lowest price ranked as 1st in the amount of USD 10,000 = a

- Offeror B – second lowest price ranked as 2nd in the amount of USD 15,000 = b

Points assigned to A = 300 & Points assigned to B = 200 (following formula: a/b * 300 i.e. 10,000/15,000 * 300 = 200 points)

Option 2: Combined Technical and Financial Evaluation Form

| Sample: Summary of Financial Proposal Evaluation Forms |  | Points Obtainable | Name of Firm / Institution |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | A | B | C | D |
|  | Sub-total Technical Proposal | 700 |  |  |  |  |
|  | Sub-total Financial Proposal | 300 |  |  |  |  |
|  | Total 1000 |  |  |  |  |  |

F. AWARD OF CONTRACT

24. Award criteria, award of contract

UNESCO reserves the right to accept or reject any Proposal, and to annul the solicitation process and reject all Proposals at any time prior to award of contract, without thereby incurring any liability to the affected Offeror or any obligation to inform the affected Offeror or Offerors of the grounds for such action.

Prior to expiration of the period of proposal validity, UNESCO will award the contract to the qualified Offeror whose Proposal after being evaluated is considered to be the most responsive to the needs of the organisation and activity concerned.

25. Purchaser’s right to vary requirements at time of award and to negotiate

UNESCO reserves the right at the time of award of contract to increase or decrease by up to 20% the quantity of services and goods specified in the RFP without any change in hourly/daily or any other rates or prices proposed by the Bidders or other terms and conditions.

UNESCO reserves the right to undertake further negotiations on the proposed offer.

ANNEX II – General Terms and Conditions for Professional Services

- LEGAL STATUS

The Contractor shall be considered as having the legal status of an independent contractor vis-à-vis UNESCO. The Contractor’s personnel and sub-contractors shall not be considered in any respect as being the employees or agents of UNESCO.

- SOURCE OF INSTRUCTIONS

The Contractor shall neither seek nor accept instructions from any authority external to UNESCO in connection with the performance of its services under this Contract. The Contractor shall refrain from any action, which may adversely affect UNESCO or the United Nations and shall fulfill its commitments with the fullest regard to the interests of UNESCO.

- CONTRACTOR’S RESPONSIBILITY FOR EMPLOYEES

The Contractor shall be responsible for the professional and technical competence of its employees and will select, for work under this Contract, reliable individuals who will perform effectively in the implementation of this Contract, respect the local customs, and conform to a high standard of moral and ethical conduct.

- ASSIGNMENT

The Contractor shall not assign, transfer, pledge or make other disposition of this Contract or any part thereof, or any of the Contractor’s rights, claims or obligations under this Contract except with the prior written consent of UNESCO.

- SUB-CONTRACTING

In the event the Contractor requires the services of sub-contractors, the Contractor shall obtain the prior written approval and clearance of UNESCO for all sub-contractors. The approval of UNESCO of a sub-contractor shall not relieve the Contractor of any of its obligations under this Contract. The terms of any sub-contract shall be subject to and conform with the provisions of this Contract.

- OFFICIALS NOT TO BENEFIT

The Contractor warrants that no official of UNESCO has received or will be offered by the Contractor any direct or indirect benefit arising from this Contract or the award thereof. The Contractor agrees that breach of this provision is a breach of an essential term of this Contract.

- INDEMNIFICATION

The Contractor shall indemnify, hold and save harmless, and defend, at its own expense, UNESCO, its officials, agents, and employees from and against all suits, claims, demands, and liability of any nature or kind, including their costs and expenses, arising out of acts or omissions of the Contractor, or the Contractor’s employees, officers, agents or sub-contractors, in the performance of this Contract. This provision shall extend, inter-alia, to claims and liability in the nature of workmen’s compensation, products liability and liability arising out of the use of patented inventions or devices, copyrighted material or other intellectual property by the Contractor, its employees, officers, agents, servants or sub-contractors. The obligations under this Article do not lapse upon termination of this Contract.

- INSURANCE AND LIABILITIES TO THIRD PARTIES

The Contractor shall provide and thereafter maintain insurance against all risks in respect of its property and any equipment used for the execution of this Contract. The Contractor shall provide and thereafter maintain all appropriate workmen’s compensation insurance, or its equivalent, with respect to its employees to cover claims for personal injury or death in connection with this Contract. The Contractor shall also provide and thereafter maintain liability insurance in an adequate amount to cover third party claims for death or bodily injury, or loss of or damage to property, arising from or in connection with the provision of services under this Contract or the operation of any vehicles, The Contractor shall provide and thereafter maintain all appropriate workmen's compensation insurance, or its equivalent, with respect to its employees to cover claims for personal injury or death in connection with this Contract or the operation of any vehicles, boats, airplanes or other equipment owned or leased by the Contractor or its agents, servants, employees or sub-contractors performing work or services in connection with this Contract. Except for the workmen’s compensation insurance, the insurance policies under this Article shall:

8.1 Name UNESCO as additional insured;

8.2 Include a waiver of subrogation of the Contractor’s rights to the insurance carrier against UNESCO;

8.3 Provide that UNESCO shall receive thirty (30) days written notice from the insurers prior to any cancellation or change of coverage8.4 The Contractor shall, upon request, provide UNESCO with satisfactory evidence of the insurance required under this Article.

### ENCUMBRANCES/LIENS

The Contractor shall not cause or permit any lien, attachment or other encumbrance by any person to be placed on file or to remain on file in any public office or on file with UNESCO against any monies due or to become due for any work done or materials furnished under this Contract, or by reason of any other claim or demand against the Contractor.

- TITLE TO EQUIPMENT

Title to any equipment and supplies that may be furnished by UNESCO shall rest with UNESCO and any such equipment shall be returned to UNESCO at the conclusion of this Contract or when no longer needed by the Contractor. Such equipment, when returned to UNESCO, shall be in the same condition as when delivered to the Contractor, subject to normal wear and tear. The Contractor shall be liable to compensate UNESCO for equipment determined to be damaged or degraded beyond normal wear and tear.

- COPYRIGHT, PATENTS AND OTHER PROPRIETARY RIGHTS

UNESCO shall be entitled to all intellectual property and other proprietary rights including but not limited to patents, copyrights, and trademarks, with regard to products, or documents and other materials which bear a direct relation to or are produced or prepared or collected in consequence of or in the course of the execution of this Contract. At UNESCO’s request, the Contractor shall take all necessary steps, execute all necessary documents and generally assist in securing such proprietary rights and transferring them to UNESCO in compliance with the requirements of the applicable law

- USE OF NAME, EMBLEM OR OFFICIAL SEAL OF UNESCO OR THE UN

The Contractor shall not advertise or otherwise make public the fact that it is a Contractor with UNESCO, nor shall the Contractor, in any manner whatsoever use the name, emblem or official seal of UNESCO, or any abbreviation of the name of UNESCO in connection with its business or otherwise.

13. CONFIDENTIAL NATURE OF DOCUMENTS AND INFORMATION

Information and data that is considered proprietary by either Party or that is delivered or disclosed by one Party (“Discloser”) to the other Party (“Recipient”) during the course of performance of the Contract, and that is designated as confidential (“Information”), shall be held in confidence by that Party.

Drawings, photographs, plans, reports, recommendations, estimates, documents and all other data compiled by or received by the Contractor under this Contract shall be the property of UNESCO, shall be treated as confidential and shall be delivered only to UNESCO authorized officials on completion of work under this Contract. The Contractor may not communicate at any time to any other person, Government or authority external to UNESCO, any information known to it by reason of its association with UNESCO, which has not been made public except with the authorization of UNESCO; nor shall the Contractor at any time use such information to private advantage. These obligations do not lapse upon termination of this Contract.

UNESCO may disclose Information to the extent required pursuant to resolutions or regulations of the General Conference or rules promulgated thereunder and to the UNESCO Access to Information policy. The Contractor acknowledges that UNESCO’s Information, including any information relating to an identified or identifiable individual (“Personal Data”), is subject to privileges and immunities accorded to UNESCO and that as a result any such Information is inviolable and cannot be disclosed, provided or otherwise made available to, or searched, confiscated or otherwise be interfered with by any person, unless such immunity is expressly waived in writing by UNESCO. To ensure compliance with the privileges and immunities of UNESCO, the Contractor shall segregate Information provided by UNESCO or generated by the Contractor under this Contract to the fullest extent possible.

14. FORCE MAJEURE; OTHER CHANGES IN CONDITIONS

Force majeure, as used in this Article, means acts of God, war (whether declared or not), invasion, revolution, insurrection, or other acts of a similar nature or force, which are beyond the control of the Parties. In the event of and as soon as possible after the occurrence of any cause constituting force majeure, the Contractor shall give notice and full particulars in writing to UNESCO, of such occurrence or change if the Contractor is thereby rendered unable, wholly or in part, to perform its obligations and meet its responsibilities under this Contract. The Contractor shall also notify UNESCO of any other changes in conditions or the occurrence of any event, which interferes or threatens to interfere with its performance of this Contract. The notice shall include steps proposed by the Contractor to be taken including any reasonable alternative means for performance that is not prevented by force majeure. On receipt of the notice required under this Article, UNESCO shall take such action as, in its sole discretion, it considers to be appropriate or necessary in the circumstances, including the granting to the Contractor of a reasonable extension of time in which to perform its obligations under this Contract. If the Contractor is rendered permanently unable, wholly, or in part, by reason of force majeure to perform its obligations and meet its responsibilities under this Contract, UNESCO shall have the right to suspend or terminate this Contract on the same terms and conditions as are provided for in Article 15, “Termination”, except that the period of notice shall be seven (7) days instead of thirty (30) days.

15. TERMINATION

Either party may terminate this Contract for cause, in whole or in part, upon thirty days notice, in writing, to the other party. The initiation of arbitral proceedings in accordance with Article 16 “Settlement of Disputes” below shall not be deemed a termination of this Contract. UNESCO reserves the right to terminate without cause this Contract at any time upon 15 days prior written notice to the Contractor, in which case UNESCO shall reimburse the Contractor for all reasonable costs incurred by the Contractor prior to receipt of the notice of termination. In the event of any termination by UNESCO under this Article, no payment shall be due from UNESCO to the Contractor except for work and services satisfactorily performed in conformity with the express terms of this Contract. The Contractor shall take immediate steps to terminate the work and services in a prompt and orderly manner and to minimize losses and further expenditures. Should the Contractor be adjudged bankrupt, or be liquidated or become insolvent, or should the Contractor make an assignment for the benefit of its creditors, or should a Receiver be appointed on account of the insolvency of the Contractor, UNESCO may, without prejudice to any other right or remedy it may have, terminate this Contract forthwith. The Contractor shall immediately inform UNESCO of the occurrence of any of the above events.

- SETTLEMENT OF DISPUTES

  - Amicable Settlement

The Parties shall use their best efforts to settle amicably any dispute, controversy or claim arising out of, or relating to this Contract or the breach, termination or invalidity thereof. Where the parties wish to seek such an amicable settlement through conciliation, the conciliation shall take place in accordance with the UNCITRAL Conciliation Rules then obtaining, or according to such other procedure as may be agreed between the parties.

  - Arbitration

Unless, any such dispute, controversy or claim between the Parties arising out of or relating to this Contract or the breach, termination or invalidity thereof is settled amicably under the preceding paragraph of this Article within sixty (60) days after receipt by one Party of the other Party’s request for such amicable settlement, such dispute, controversy or claim shall be referred by either Party to arbitration in accordance with the UNCITRAL Arbitration Rules then obtaining, including its provisions on applicable law. The arbitral tribunal shall have no authority to award punitive damages. The Parties shall be bound by any arbitration award rendered as a result of such arbitration as the final adjudication of any such controversy, claim or dispute.

17. PRIVILEGES AND IMMUNITIES

Nothing in or relating to this Contract shall be deemed a waiver, express or implied, of any of the privileges and immunities of UNESCO.

18. TAX EXEMPTION

18.1 	Section 7 of the Convention on the Privileges and Immunities of the United Nations provides, inter-alia, that UNESCO, is exempt from all direct taxes, except charges for public utility services, and is exempt from customs duties and charges of a similar nature in respect of articles imported or exported for its official use. In the event any governmental authority refuses to recognize the UNESCO exemption from such taxes, duties or charges, the Contractor shall immediately consult with UNESCO to determine a mutually acceptable procedure.

18.2 	Accordingly, the Contractor authorizes UNESCO to deduct from the Contractor’s invoice any amount representing such taxes, duties or charges, unless the Contractor has consulted with UNESCO before the payment thereof and UNESCO has, in each instance, specifically authorized the Contractor to pay such taxes, duties or charges under protest. In that event, the Contractor shall provide UNESCO with written evidence that payment of such taxes, duties or charges has been made and appropriately authorized.

19. CHILD LABOUR

  - The Contractor represents and warrants that neither it, nor any of its suppliers is engaged in any practice inconsistent with the rights set forth in the Convention on the Rights of the Child, including Article 32 thereof, which, inter-alia, requires that a child shall be protected from performing any work that is likely to be hazardous or to interfere with the child’s education, or to be harmful to the child’s health or physical mental, spiritual, moral or social development.

  - Any breach of this representation and warranty shall entitle UNESCO to terminate this Contract immediately upon notice to the Contractor, at no cost to UNESCO.

20. MINES

  - The Contractor represents and warrants that neither it nor any of its suppliers is actively and directly engaged in patent activities, development, assembly, production, trade or manufacture of mines or in such activities in respect of components primarily utilized in the manufacture of Mines. The term “Mines” means those devices defined in Article 2, Paragraphs 1, 4 and 5 of Protocol II annexed to the Convention on Prohibitions and Restrictions on the Use of Certain Conventional Weapons Which May Be Deemed to Be Excessively Injurious or to Have Indiscriminate Effects of 1980.

20.2 	Any breach of this representation and warranty shall entitle UNESCO to terminate this Contract immediately upon notice to the Contractor, without any liability for termination charges or any other liability of any kind of UNESCO.

21. OBSERVANCE OF THE LAW

The Contractor shall comply with all laws, ordinances, rules, and regulations bearing upon the performance of its obligations under the terms of this Contract.

22. AUTHORITY TO MODIFY

No modification or change in this Contract, no waiver of any of its provisions or any additional contractual relationship of any kind with the Contractor shall be valid and enforceable against UNESCO unless provided by an amendment to this Contract signed by the authorized official of UNESCO.

23. SECURITY

The responsibility for the safety and security of the Contractor and its personnel and property, and of UNESCO property in the Contractor’s custody, rests with the Contractor.

The Contractor shall:
(a) put in place an appropriate security plan and maintain the security plan, taking into account the security situation in the country where the services are being provided;

(b) assume all risks and liabilities related to the Contractor’s security, and the full implementation of the security plan.

UNESCO reserves the right to verify whether such a plan is in place, and to suggest modifications to the plan when necessary. Failure to maintain and implement an appropriate security plan as required hereunder shall be deemed a breach of this contract. Notwithstanding the foregoing, the Contractor shall remain solely responsible for the security of its personnel and for UNESCO property in its custody.

24. ANTI-TERRORISM

The Contractor agrees to undertake all reasonable efforts to ensure that none of the UNESCO funds received under this Contract are used to provide support to individuals or entities associated with terrorism and that the recipients of any amounts provided by UNESCO hereunder do not appear on on the list maintained by the Security Council Committee established pursuant to resolution 1267 (1999). The list can be accessed via: 
https://www.un.org/sc/suborg/en/sanctions/un-sc-consolidated-list.

This provision must be included in all sub-contracts or sub-agreements entered into under the Contract.

25. AUDITS AND INVESTIGATIONS:

Each invoice paid by UNESCO shall be subject to a post-payment audit by auditors, whether internal or external, of UNESCO or by other authorized and qualified agents of UNESCO at any time during the term of the Contract and for a period of three (3) years following the expiration or prior termination of the Contract.

UNESCO may conduct investigations relating to any aspect of the Contract or the award thereof, the obligations performed under the Contract, and the operations of the Contractor generally relating to performance of the Contract at any time during the term of the Contract and for a period of three (3) years following the expiration or prior termination of the Contract.

The Contractor shall provide its full and timely cooperation with any such post payment audits or investigations. Such cooperation shall include, but shall not be limited to, the Contractor’s obligation to make available its personnel and any relevant documentation for such purposes at reasonable times and on reasonable conditions and to grant to UNESCO access to the Contractor’s premises at reasonable times and on reasonable conditions in connection with such access to the Contractor’s personnel and relevant documentation. The Contractor shall require its agents, including, but not limited to, the Contractor’s attorneys, accountants or other advisers, to reasonably cooperate with any post-payment audits or investigations carried out by UNESCO hereunder.

UNESCO shall be entitled to a refund from the Contractor for any amounts shown by audits or investigations to have been paid by UNESCO other than in accordance with the terms and conditions of the Contract.

26. PROTECTION FROM SEXUAL EXPLOITATION AND SEXUAL ABUSE

Definitions. For purposes of the Contract, “sexual exploitation” means any actual or attempted abuse of a position of vulnerability, differential power, or trust, for sexual purposes, including, but not limited to, profiting monetarily, socially or politically from the sexual exploitation of another; “sexual abuse” means the actual or threatened physical intrusion of a sexual nature, whether by force or under unequal or coercive conditions. Sexual exploitation and abuse are strictly prohibited. The Contractor, its employees, agents or any other persons engaged by the Contractor to perform any services under the Contract, shall not engage in any sexual exploitation and abuse. The Contractor acknowledges and agrees that UNESCO will apply a policy of “zero tolerance” with regard to sexual exploitation and abuse of anyone by the Contractor, its employees, agents or any other persons engaged by the Contractor to perform any services under the Contract.

Without prejudice to the generality of the foregoing:

(a) Sexual activity with a child (any person less than eighteen years of age), regardless of any laws relating to the age of majority or to consent, shall constitute the sexual exploitation and abuse of such person. Mistaken belief in the age of a child shall not constitute a defense under the Agreement.

(b) The exchange or promise of exchange of any money, employment, goods, services, or other thing of value, for sex, including sexual favors or sexual activities, shall constitute sexual exploitation and abuse.

(c) The Contractor acknowledges and agrees that sexual relationships between the Contractor’s employees, agents or other persons engaged by the Contractor and beneficiaries of assistance, since they are based on inherently unequal power dynamics, undermine the credibility and integrity of the work of UNESCO and are strongly discouraged.

Reporting of allegations to UNESCO. The Contractor shall report allegations of sexual exploitation and abuse, of which the Contractor has been informed or has otherwise become aware, promptly to UNESCO, in line with its established reporting mechanism. To the extent legally possible, the Contractor will require its employees, agents or any other persons engaged by the Contractor to perform any services under the Contract, to report allegations of sexual exploitation and abuse arising in relation to the Contract directly to UNESCO.

This provision must be included in all sub-contracts or sub-agreements entered into under the Contract.

27. UNITED NATIONS SUPPLIER CODE OF CONDUCT

The Contractor acknowledges  that the UN Supplier Code of Conduct (available from https://www.un.org/Depts/ptd/about-us/un-supplier-code-conduct) provides the minimum standards expected of the UN Suppliers.

28. PERSONAL DATA PROTECTION AND PRIVACY

Both UNESCO and the Contractor shall ensure an appropriate protection of Personal Data in accordance with UNESCO’s Principles on Personal Data Protection and Privacy (https://www.unesco.org/en/privacy-policy) and their applicable regulations and rules. Personal Data shall be processed solely for the purpose of undertaking this Contract.

The Contractor warrants and represents that it shall establish and maintain appropriate technical and organizational measures against accidental or unlawful destruction or accidental loss, alteration, unauthorized disclosure or access to Personal Data in compliance with best industry standards.

The Contractor shall promptly notify UNESCO of any actual [or suspected or threatened] incident of accidental or unlawful Initials destruction or accidental loss, alteration, unauthorized or accidental disclosure or access to Personal Data, or a breach of this article. The Parties shall consult with a view to addressing, reacting to, and resolving the situation.

The Contractor shall notify UNESCO within five working days of any complaint by an individual in respect of his/her Personal Data. The Parties shall consult with each other before taking any action as a result of or in reaction to such complaint.

The obligations and restrictions in this Article shall be effective during the term of this Contract, including any extension thereof, and shall remain effective following any termination of this Contract, unless otherwise agreed between the Parties in writing.

Unless otherwise agreed between the Parties in writing, after termination of this Contract the Contractor shall return all Personal Data collected for the performance of this Contract to UNESCO in a structured, commonly used and machine-readable format, and shall then delete and procure the deletion of all copies of that Personal Data. The Contractor shall provide written certification to UNESCO that it has fully complied with this paragraph after termination of this Contract.

#### ANNEX III – Terms of Reference (TOR)

- Background:

UNESCO is actively involved in the Global Partnership for Education-Education Sector Programme Implementation Grant (GPE-ESPIG) programme. The primary objective of the GPE-ESPIG programme is to ensure that the most marginalized children, including those who are out-of-school or at risk of dropping out, gain access to quality learning opportunities. These opportunities are crucial for them to acquire relevant skills, build resilience, continue their education, and enhance their overall well-being. The GPE-ESPIG programme consists of three key components:

- Access: focuses on facilitating safe and equitable access to learning for children and youth in Myanmar.

- Quality: aims to ensure quality teaching and learning experiences for children and youth in Myanmar. This involves strengthening the capacities of education personnel and fostering context-responsive, equity-focused learning resources and modalities that adapt to the evolving situation.

- System Strengthening: places emphasis on strengthening systems, management, coordination, and monitoring related to education in Myanmar.

These outcomes contribute to the long-term goal of ESPIG, which is to ensure that children and youth in Myanmar can engage in quality, meaningful, inclusive, and gender-responsive learning in safe, protective environments, particularly focusing on the most vulnerable learners. To advance these goals, UNESCO is developing the Myanmar Youth Platform to provide self-learning opportunities and enhance employment prospects for out-of-school children and youth in Myanmar. And the platform will offer a range of online courses such as personal development, career development, financial literacy, digital literacy, health and well-being, entrepreneurship, language, vocational courses. To support these initiatives, UNESCO Antenna Office in Yangon is currently seeking the Organizations or legal entities which will develop the education content at Myanmar Youth Platform.

- Work Assignment:

Under the overall authority of the Regional Director of UNESCO Regional Office in Bangkok, the direct supervision of the Head of UNESCO Antenna Office in Yangon, and in close collaboration with Education unit, the following tasks must be carried out:

- Desk Review and Course Content Mapping

- Conduct a comprehensive desk review of existing online courses, curriculum and training materials, focusing particularly on following vocational courses.

    - Mobile Phone Repair

    - Computer Repair

    - Handmake craft and accessories

    - Plumbing & Pipe Repair

    - Baking & Pastry Making

    - Basic Music Skill

- Engage in discussions and consultations with UNESCO to understand the functionalities and structures of UNESCO platform and other relevant online course development tools.

- Develop the detailed course content map  for each course , including course overview, learning outcome, course structure, lessons breakdown and assessment plan.

- Online Course Development

- For each course, develop at least five one-hour modules.   Content components include course overview, objectives, format, content delivery methods and engagement activities (e.g., videos, quizzes, interactive activities).

- Develop detailed course content including  narration scripts for audio and video lessons,  interactive exercises, case studies, and scenario-based activities to enhance engagement and incorporating quizzes and assessments.

- Share draft content with UNESCO for review and incorporate feedback, adjusting course content, instructional methods, or content clarity as needed.

- Develop the multimedia lessons ( e.g video, audio, graphic) based on the final course content.

- Use suitable online course creation tools (H5P, Articulate Storyline, etc )  to accommodate  interactive content (e.g., videos, audio and interactive quiz). Ensure all course content is compatible with the Myanmar Youth Platform’s technical infrastructure.

- Conduct Pilot Testing and Launching the Courses at Platform

- Upload the draft online courses to the Myanmar Youth Platform by coordinating with platform administrators to ensure the smooth integration of courses into the platform.

- Conduct a pilot test with at least 50 participants per course, representing the target audience of adolescents. Collect detailed feedback on the usability, accessibility, and effectiveness of each course.

- Revise and enhance the online courses based on pilot testing results. Produce the final version of courses, integrating all revisions, refinements, and adjustments.

- Follow the requirements of the manuals, guidelines and intellectual property rights:

- Ensure that the online course comply with the UNESCO Style Manual (2004 version available at https://unesdoc.unesco.org/ark:/48223/pf0000141812) such as terminology, abbreviations, acronyms and format of footnotes, etc.

- Streamline UNESCO’s gender strategy, ensure the Guidelines on Gender-Neutral Language is applied throughout the online course (https://unesdoc.unesco.org/ark:/48223/pf0000377299).

- Compile a list of tables, figures (including diagram, chart, illustration), photos (including images, cartoons, icons) and other graphic elements from the third party-materials by using a template provided by UNESCO.

- Secure the intellectual property rights by using the “permission consent form” (provided by UNESCO) to obtain a written authorization from the original source of work when include the third-party materials and inform them regarding UNESCO Open Access Policy.

- Ensure that no plagiarized or self-plagiarized material is published without appropriate acknowledgement of the source.

- Provide a proper credit or citation to the original work of the third-party materials. For any materials created by author, the “Source: author” should be placed underneath aforementioned materials.

- Use standard video editing software most suitable for the production and finalize in the later stages of development. Recommended software includes Adobe Premiere Pro and Final Cut Pro.

- Propose to and agree with UNESCO on the selection of the video’s narrator(s) (if needed) and cast and record the voice-over narration in Myanmar language based on UNESCO's final decision. Secure the authorization from the narrator on behalf of UNESCO by using the Grant of Rights form.

- Suggest a choice of background music to UNESCO and obtain necessary usage rights on the final choice. Synchronize voice-music-images/mix sound (Grant of Rights form to be provided by UNESCO).

- Obtain permission from the photographed/videographed persons by having them signed a consent form (provided by UNESCO).

- Include the UNESCO video outro: https://trello.com/c/ieHy4KQR/74-english if UNESCO is the only party involved in this project.

- Ensure that the online course and video are in full compliance with the international copyrights policy to avoid any illegal consequence as outline in the ‘general terms and conditions’ which annexed in this contract.

- Strictly treat the online courses confidential and the rights of distribution will reside solely with UNESCO.

- Submit the video in MP4 format with subtitles to UNESCO for review and feedback.

- Incorporate suggested changes and finalize video as needed.

- Submit the editable source/master file (including video graphic files) for archiving.

- Strictly meet the committed deadline.

- Provide the video with the following specifications:

| Item | Technical specifications |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Ratio | Codec | Frame Rate | Audio bitrate | Video format |
| HD Video | 16:9 | H.264 | 24-30 fps | 160-192 kbps | Video format MP4 Video Size 1920x1080 (HD) |
| SD Video | 16:9 | H.264 | 18-20 fps | 96-128 kbps | Video format MP4 Video Size 1280x720 |

- Deliverables and Timeline:

All deliverables must be submitted with original/editable files, as well as high-resolution versions of final products (if applicable) to UNESCO. The assigned tasks must be submitted by the following deadlines.

| Deliverables | Deadlines |
| --- | --- |
| - Submit the detailed course content map for each course , including course overview, learning outcome, course structure, lessons breakdown and assessment plan. | 30 July 2025 |
| - Submit the draft version of course content (6 courses) to UNESCO for review. | 30 September 2025 |
| - Submit the final version of course content (6 courses) to UNESCO for approval. | 28 October 2025 |
| - Submit the first version of interactive online courses (6 courses), including the video per specification indicated in item II (r) to UNESCO for review. | 15 December 2026 |
| - Submit the revised version of interactive online courses (6 courses), including the video as per specification indicated in item II (r) to UNESCO for approval. - Submit the pilot testing plan with at least 50 participants for each course. | 30 January 2026 |
| - Submit the pilot testing report and the final 6 interactive online courses, uploaded at Myanmar Youth Platform. | 28 February 2026 |

- Minimum content of proposals:

Please refer to ANNEX I – Instructions to Offerors for guidelines and instructions on the preparation, clarification, and submission of Proposals. At minimum, technical proposals should include the following:

- Proposal including description of the firm/institution and its qualifications: Please include evidence to support that mandatory and desirable requirement, as outlined below, are met. This evidence should include a record of international education development experience, references of previous clients, and samples of previous work related to education or other social sector policy, planning and finance from an international perspective.

- Proposed Approach, Methodology, Timing and Outputs: The technical proposal should consider the key activities as per TOR based on the Firm/Institution’s own interpretation as well as strategies in achieving the expected outcomes and stakeholders to be involved in the different activities. And the proposal should include:

- Realistic workplan with specific treatment of key deliverables and priorities as well as clear repartition of tasks amongst team members,

- Risk Management Plan (RMP) including identification of risks and mitigation measures to be undertaken for each required deliverable, highlighting specific risks and mitigation strategies for each step of the project.

- Proposed Personnel: Please include CVs for all personnel.

- A separate price proposal providing a detailed cost breakdown, is also required as per ANNEX V - Price Schedule Form and must be submitted in separately from the technical proposal sent through a separate email (in a password protected file). Costs associated with carrying out the development of online course, such as recording, narrator/sign language personnel’s fee, printing, office supplies, and any required hardware, should be included in the price proposal.

- Eligibility/qualification/experience requirements:

Eligible organizations are international or national NGOs, foundations, firm, company, and similar institutions/ organizations. Firms/institutions are required to provide evidence that support the mandatory and relevant desirable criteria are met. Failure to meet any mandatory criterion will lead to the disqualification of the proposal. According to the evaluation grid, proposals with additional references/proof of evidence to the minimum requirements shall receive higher scores.

THE FIRM/INSTITUTION

Required Qualifications (mandatory):

- Demonstrated expertise in developing and delivering vocational courses, particularly in areas such as mobile phone repair, computer repair, crafting, baking, and music skills.

- Established capabilities in developing online courses using Learning Management Systems (LMS), such as Moodle, Canvas, or similar platforms.

- Expertise in developing interactive and engaging multimedia content, with various eLearning authoring tools such as H5P, Articulate Storyline, Adobe Captivate, and other interactive course creation tools.

- Expertise in ensuring courses are compatible with various devices, including mobile phones and low-bandwidth environments.

Desirable Qualifications:

- Prioritizes inclusivity, gender equality and cultural relevance by creating content accessible to learners with disabilities, incorporating features such as sign language, subtitling, and alternative text formats as well as developing cultural relevant and gender balanced characters.

PERSONNEL

Lead personnel/staff to implement the activities:

Required Qualifications (mandatory):

- Holds a master’s degree in education or a related field, with over 8 years of experience managing education programs/projects.

- Led the development of at least three large-scale education projects of online learning solutions for out-of-school children in Myanmar.

- At least 5 years of experiences to oversee and align multiple project components, from course development to pilot testing and final implementation.

Desirable Qualifications:

- Demonstrated success in managing projects that incorporate input from marginalized communities.

Team member/staff to co-implement the activities with the lead personnel:

Required Qualifications (mandatory):

- Instructional Designer with at least 4 years of experience in curriculum design, interactive content creation, and instructional strategies for digital platforms.

- Technical Specialist with at least 4 years of experiences in LMS integration, multimedia production, and e-learning tools.

- Content Developer with at least 4 years of experiences in creating accessible, engaging learning materials, including quizzes, case studies, and video scripts.

- Quality Assurance (QA) Specialist with at least 4 years of experience in testing and evaluating e-learning platforms, ensuring the technical functionality, usability, and accessibility of online courses.

Desirable Qualifications:

#### Familiarity with developing content for learners with disabilities, including tactile, auditory, and visual learning aids.

#### ANNEX IV – Proposal Submission Form

TO: UNESCO

To form an integral part of your technical proposal

Dear Sir / Madam,

Having examined the Solicitation Documents, the receipt of which is hereby duly acknowledged, we, the undersigned, offer to provide Professional Services for the sum as may be ascertained in accordance with the Price Schedule attached herewith and made part of this Proposal.

We undertake, if our Proposal is accepted, to commence and complete delivery of all services specified in the contract within the time frame stipulated.

We agree to abide by this Proposal for a period of 90 days from the Proposal Closing Date as stipulated in the Solicitation Documents, and it shall remain binding upon us and may be accepted at any time before the expiration of that period.

We understand that you are not bound to accept any Proposal you may receive.

| Name of Bidder: |  |
| --- | --- |
| Address of Bidder: |  |
| Authorised Signature: |  |
| Name & title of Authorised Signature: |  |
| Date: |  |

# ANNEX V – Price Schedule Form

GENERAL INSTRUCTIONS

1. The Bidder is asked to prepare the Price Schedule as a separate envelope from the rest of the RFP response as indicated in paragraph 16 (b) of the Instructions to Offerors.

2. All prices/rates quoted must be exclusive of all taxes, since the UNESCO is exempt from taxes as detailed in Annex II, Clause 18.

3. The Price Schedule must provide a detailed cost breakdown. Provide separate figures for each functional grouping or category. If the contractor is required to travel in order to perform the work described in the TOR, a lump sum must be included in the total amount or to be listed separately. No travel shall be reimbursed.

4. It is the policy of UNESCO not to grant advance payments except in unusual situations where the potential contractor whether a private firm, NGO or a government or other entity, specifies in the proposal that there are special circumstances warranting an advance payment. UNESCO, at its discretion, may however determine that such payment is not warranted or determine the conditions under which such payment would be made.

Any request for an advance payment is to be justified and documented and must be submitted with the financial proposal. This justification shall explain the need for the advance payment, itemise the amount requested and provide a time-schedule for utilisation of said amount.

| Financial Proposal / Price Schedule Request for Proposal Ref: Total Financial Proposal [currency/amount]: Date of Submission: Authorized Signature: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Description of Activity/Item |  | No of staffs/ participants | Rate per month [currency/ amount] | No of man-days/month | Total [currency/amount] |
| 1. | Desk Review and Course Content Mapping |  |  |  |  |
| 1.1 | Comprehensive review of the existing related courses and resources |  |  |  |  |
| 1.2 | Course content mapping |  |  |  |  |
| 1.5 | Others (please specify) |  |  |  |  |
| Description of Activity/Item |  | No of participants /staffs | Rate per Day [currency/ amount] | No of man-days | Total [currency/amount] |
| 2.. | Online Course Development |  |  |  |  |
| 2.1 | Create course objectives, structure, and delivery methods Draft narration scripts, interactive exercises, case studies, and assessment |  |  |  |  |
| 2.2 | Use content creation tools (e.g., videos, quizzes, interactive modules) |  |  |  |  |
| 2.3 | Refine and adjust course content based on UNESCO feedback |  |  |  |  |
| 2.4 | Upload the courses to the Myanmar Youth Platform |  |  |  |  |
| 2.5 | Others (please specify) |  |  |  |  |
| Description of Activity/Item |  | No of participants /staffs | Rate per Day [currency/ amount] | No of man-days | Total [currency/amount] |
| 3. | Conduct Pilot Testing and Launching the Courses |  |  |  |  |
| 3.1 | Organize pilot testing with at least 50 participants Collect feedback on usability, accessibility, and engagement |  |  |  |  |
| 3.2 | Analyze feedback and refine courses based on pilot results |  |  |  |  |
| 3.3 | Others ( please specify) |  |  |  |  |

# ANNEX VI – Vendor Information Form

General Information

| Company Name: |  |
| --- | --- |
| City, Country |  |
| Web Site URL: |  |
| Contact Person: |  |
| Title: |  |
| Phone: |  |
| Email Address: |  |

Expertise of the Bidder

| Line of Business, area of expertise: |  |
| --- | --- |
| Type of business (manufacturer, distributor, etc): |  |
| Years of company experience: |  |
| Main export countries/area: |  |
| Past Contracts with other UN organizations: |  |

References: Please provide at least three references including contact details for contracts for similar services to the one requested under this consultancy:

| Organization Name/Country: | Contact person: | Telephone: | Email: |
| --- | --- | --- | --- |
| 1. |  |  |  |
| 2. |  |  |  |
| 3. |  |  |  |