**INTER-AGENCY MULTISECTORAL RAPID ASSESSMENT PLAN**

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **State** | **Townships** | **Team leader** | | **Contact** | **Team members** | **Tentative Location** | **Tentative Date** | **Comments** |
| **Org** | **Staff Name** |
| **Sagaing** (aprox 4 teams made of 3/4 members) | Kale, Kyunhla, Kawlin, Kanbalu | OCHA | Moe Aung,  Head Bhamo SO | 09-8602829,  [moe.aung.13@gmail.com](mailto:moe.aung.13@gmail.com) | UNICEF/Khaing Khaing Shwe  WHO/Dr Tin Swe  WHO/Dr Nyunt Sein  WHO/Dr Aung Ko Ko Hein  WHO/ Chaw Su Hlaing  UNFPA/Dr Win Aung  UNDP/Kyaw Swar Lwin  UNDP/Kyi Zaw Lwin  UNDP/Aung Tin Moe  WV/Ngum Za Liam  UNICEF/Tin Htut  UNICEF/Mra Thuzar  UNICEF/Shwe Hla Oo  UNICEF/Khin Mar Win  MSI/  KMSS/  Ayaryone Oo/  MRCS/  Zomi Youth Association | Kale | 10 Aug | Meeting w authorities postponed for tomorrow 11Aug. Teams already started assessments (4 teams) in Kale and planned to be finalized by tomorrow.  Access to affected villages challenging with roads covered with mud and sediments. Some creeks divert their waterway and local authorities and community are constructing temporary bamboo bridges to cross newly appeared waterways. Water receded in almost all flooded villages. Villages are also covered with muds and sediments (at some villages 3 to 4 feet high) Some people from those villages are still staying in evac centers in town and villages. Some are constructing makeshift bamboo huts along motor roads. |
| Kale | 9/10 Aug | Assessments ongoing |
| Mandalay | 12 Aug | Team to arrive in Mandalay, mission preparations |
| Kawlin, Kanbalu, Kyunhla | 13/15 Aug | Assessments in these locations |
| **Magway** (TBC) | Saytottata, Pyint Phyu | UNDP | Aung Linn,  Area office coordinator | 095280810,  Aung.linn@undp.org | UNICEF/Thida Seine  WHO/Dr Kyaw Min Thein  WHO/Dr Kyi Thar Loon  SC/Swe Linn Maung  WV/Ngum Za Liam  WFP/Nay Win  UNDP/Hla Aung Myint  UNDP/Win Naing  UNDP/Chaw Su Khin  UNDP/Yan Naing Tun  UNDP/Khin Maung Lwin  UNFPA/Dr Aung Thu Tun  NAG/Wai Lin Cho | Magway | 10 Aug | Team members’ arrival, briefing, meeting authorities and stakeholders. Proposed assessments in Sidoktaya and Pwintbyu but needed to be revised as there are townships with higher number of population affected. |
| Sidoktaya | 11/15 Aug |  |
| Pyint Phyu | 11/15 Aug |  |
| **Chin** (TBC) | Hakha | UNICEF | Mohammad Badrul Hassan,  Chief Hakha FO | 09-250344964  mbhassan@unicef.org | WHO/Dr Wai Yan Yee Mon  WHO/Dr Aung Ye Phone  UNICEF/Biak Sung  UNICEF/Myo Min Lwin  UNDP/ Aung Paing  UNFPA/Dr Tay Zar Soe  WV/ Vum Liam Thawng  MSI/Sanda Lin  MSI/Ah Yon Oo  UNHCR/ Hau Lam Vung  CPTC/Tluang Ceu  CARD/ Daw Ngai Man  CAD/Thang Cin Lian  Green/ Anthony Cung Mang  KMSS/James Ngun Hre  UNICEF/Piang Sung Mung  UNICEF/Kap Za Lyan  UNICEF/Hein Latt  UNICEF/Ngin Tung Nung ADRA/  KMSS/Ca Hu  SC/Phone Thant | Hakha | 10 Aug | Meeting called by Chin government. CM asked for assessments in **ALL** townships and further discussions from 11 Aug. With current staff for assessment, capacity to cover besides Hakha, Tonzang, Tedim and Matupi. Need to discuss with INGO in Paletwa (ACF + IRC) feasibility of MIRA assessments as it is one of the most affected + inaccessible townships |
|  |  |  |
| **Ayeyarwaddy** | Nyaungdon, Zalun, Danuphyu, Hinthada | WFP | Kyaw Kyaw Lwin | 09788030715 | WFP/  UNICEF/Kyaw Lwin Latt, UNICEF/Theingi Soe  UNICEF/Aye Aye Kyu  UNICEF/Htoot Min |  | 7 to 10/11 Aug |  |
| **Bago** | Moe Nyo | WFP | Ma Chan |  | UNICEF/Kyaw Win Oo  UNICEF/Myo Min Soe UNFPA/Dr Seng Aung Sein Myint |  | 9 to 11/12 Aug |  |